Renewed Life International

# Website Rebuild Project Tracker

Master working document for the redesign and upgrade of renewedlifeint.com

| Project | Renewed Life International Website Upgrade |
| --- | --- |
| Current phase | Between Phase 5 (wireframes/UX) and Phase 6 (frontend build) |
| Primary goal | Build a modern, welcoming, mobile-first church website that helps visitors believe, belong, and become |
| Main benchmark direction | Meta Church structure with selected inspiration from Life.Church |

Prepared as a project control tracker to guide planning, execution, content, design, build, launch, and post-launch improvement.

# 1. Executive Snapshot

This tracker is the control document for the full website rebuild project. It shows what has already been completed, what remains, how the work is grouped into phases, what deliverables are expected in each phase, and what the immediate priorities should be next.

## Project outcome targets

Present Renewed Life as a modern, trustworthy, Spirit-filled church with a clear first-visitor journey.

Improve the homepage so the next steps are obvious: Plan Your Visit, Watch Online, Connect, and Give.

Create a strong content structure for ministries, sermons, events, and church information.

Ensure the final website is mobile-first, fast, easy to update, and ready for future growth.

## Current project status

| Area | Status | What is done | What is next |
| --- | --- | --- | --- |
| Benchmarking | Completed | Top church website patterns reviewed; benchmark direction selected. | Use findings as design and content standard. |
| Site structure | Partly complete | Core pages established in the first prototype. | Finalize navigation, page goals, and deeper page hierarchy. |
| Content planning | In progress | Initial messaging direction has been identified. | Write polished page-by-page copy and gather church assets. |
| Visual design | In progress | A clean first version exists. | Apply final branding, spacing system, imagery style, and UI polish. |
| Development | Started | A working Next.js starter has been built and run locally. | Refine components, add sections, and move to production quality. |

# 2. Phase-by-Phase Tracker

The table below maps the full project from research to post-launch improvement.

| # | Phase | Status | Purpose | Key deliverables | Immediate focus |
| --- | --- | --- | --- | --- | --- |
| 1 | Discovery and benchmarking | Done | Research excellent church websites and define the upgrade direction. | Benchmark notes; gap analysis; preferred model. | Use insights as quality benchmark. |
| 2 | Strategy and site architecture | Partly done | Define sitemap, navigation, audiences, and page goals. | Sitemap; nav structure; page purpose notes. | Finalize architecture. |
| 3 | Content planning and copywriting | Not complete | Prepare page copy, CTAs, FAQs, and church messaging. | Homepage copy; page copy deck; content checklist. | Write real content. |
| 4 | Branding and visual direction | Partly done | Set look and feel, colors, typography, image style, and UI language. | Mini design system; style decisions. | Finalize visual direction. |
| 5 | Wireframes and UX layout | Partly done | Map section order and visitor journey across major pages. | Wireframes; section maps; UX flow. | Refine layout decisions. |
| 6 | Frontend build | Started | Build the website in Next.js with reusable components. | Working codebase; page templates; navigation; responsive layout. | Move prototype to production quality. |
| 7 | Content population | Not started | Insert final content, photos, ministry details, and sermon assets. | Filled pages with real church content. | Gather and populate assets. |
| 8 | Integrations and functionality | Not started | Connect forms, WhatsApp, maps, YouTube, giving, and socials. | Functional visitor and contact pathways. | Implement practical tools. |
| 9 | QA and refinement | Not started | Test mobile layout, polish copy, fix issues, and improve performance. | Launch-ready website checklist. | Structured test pass. |
| 10 | Launch | Not started | Deploy the site to the production domain and verify the live environment. | Live renewedlifeint.com website. | Deployment and live verification. |
| 11 | Post-launch growth | Not started | Continue SEO, content, testimonies, events, and future improvements. | Improvement backlog and monthly review rhythm. | Growth roadmap. |

# 3. Workstreams and Detailed Task Breakdown

## A. Strategy and structure

Confirm the final sitemap and primary navigation.

Define page goals for Home, Plan Your Visit, About, Ministries, Sermons, Give, Events, and Contact.

Decide what content belongs on the homepage versus deeper pages.

## B. Content and messaging

Write strong homepage headline, subheading, and call-to-action copy.

Prepare a visitor-friendly “What to Expect” section.

Rewrite About, ministries, and giving language with a warmer and clearer tone.

Gather service times, address, contact details, and church distinctives.

## C. Design and branding

Apply the final color palette, type scale, button styles, cards, and section spacing.

Define image direction: authentic church photos, worship, prayer, family, and community life.

Ensure the design feels modern, welcoming, spiritual, and trustworthy.

## D. Development

Refine the current Next.js prototype into a scalable component-based structure.

Improve the homepage sections and supporting pages.

Prepare reusable blocks for sermons, ministries, CTA banners, testimonials, and FAQs.

## E. Integrations

Connect WhatsApp action links and contact forms.

Embed or link sermons and live stream pathways.

Add maps/location details and giving links.

Connect social platforms and practical visitor tools.

## F. Testing and launch readiness

Test all pages on mobile and desktop.

Check loading performance and accessibility basics.

Verify all buttons, forms, and links.

Do a final copy, spacing, and polish pass before launch.

# 4. Deliverables Register

| Deliverable | Description | Why it matters | Status |
| --- | --- | --- | --- |
| Benchmark report | Summary of the best church website examples and the selected direction. | Establishes the quality benchmark. | Done |
| Project tracker | This document, used as the management tracker for the full rebuild. | Keeps planning and execution aligned. | Done |
| Final sitemap | Confirmed page architecture and navigation. | Prevents confusion during content and build. | Pending |
| Copy deck | Page-by-page approved website text. | Essential before full production build. | Pending |
| Design system | Colors, typography, buttons, section styles, and UI rules. | Keeps the site consistent and professional. | Pending |
| Production-ready website | Complete responsive Next.js site. | Core build deliverable. | In progress |
| Launch checklist | QA, link checks, mobile checks, deployment tasks. | Reduces launch mistakes. | Pending |

# 5. Decisions, Risks, and Dependencies

## Key decisions already made

• The website is being rebuilt in Next.js rather than simply restyling the old site.

• The new site will focus on a strong first-visitor journey rather than a template-style homepage.

• The project direction is benchmarked against leading church websites, but adapted to Renewed Life’s current size and needs.

## Main risks to manage

| Risk | Potential impact | Mitigation action | Level |
| --- | --- | --- | --- |
| Content delays | The build can stall if final copy and photos are not ready. | Create a content checklist early and populate progressively. | Medium |
| Inconsistent branding | The site can look unfinished if visual direction is not locked. | Agree a simple design system before deeper build work. | Medium |
| Feature creep | Too many add-ons can delay launch. | Separate phase 1 essentials from phase 2 enhancements. | High |
| Weak visitor clarity | A beautiful site may still underperform if next steps are not clear. | Prioritize Plan Your Visit, service times, and obvious CTAs. | High |

## Dependencies

• Church logo files and approved brand colors

• Good-quality real photos from services, worship, leadership, families, and ministry life

• Confirmed service times, contact details, social links, and giving pathway

• Final ministry descriptions, pastor bio summary, and visitor FAQs

# 6. Immediate Next-Step Tracker

| # | Next action | Reason | Target phase |
| --- | --- | --- | --- |
| 1 | Finalize the sitemap and page priorities. | This locks the structure before deeper design/build. | Phase 2 |
| 2 | Write the homepage and Plan Your Visit copy. | These pages drive the strongest first impression. | Phase 3 |
| 3 | Confirm the visual direction and church brand cues. | This ensures the design feels intentional and consistent. | Phase 4 |
| 4 | Upgrade the current prototype into the polished production version. | The code foundation already exists. | Phase 6 |
| 5 | Load real media, contact pathways, sermons, and giving links. | The site becomes truly usable only with real content and integrations. | Phases 7–8 |

Recommended project focus right now: complete the structure, content, and visual direction decisions quickly, then continue the build with confidence. The prototype stage is already underway, so the project should now move from broad exploration into controlled execution.