Renewed Life International

Website Rebuild Project Tracker

Master working document for the redesign and upgrade of renewedlifeint.com

Project

Renewed Life International Website Upgrade

Current phase

Phase 6 (frontend build) is complete.

Phase 7 (content population) is substantially complete.

Active remaining work is concentrated in Phase 8 (integrations), Phase 9 (QA and refinement), and Phase 10 (launch preparation).

Primary goal

Build a modern, welcoming, mobile-first church website that helps visitors believe, belong, and become.

Main benchmark direction

Meta Church structure with selected inspiration from Life.Church

1. Executive Snapshot

This tracker is the control document for the full website rebuild project. It shows what has been completed, what remains, how the work is grouped into phases, and what the immediate launch priorities are now.

Project outcome targets

Present Renewed Life as a modern, trustworthy, Spirit-filled church with a clear first-visitor journey.

Make the next steps obvious: Plan Your Visit, Watch Online, Connect, and Give.

Create a strong content structure for ministries, sermons, events, and church information.

Ensure the final website is mobile-first, fast, easy to update, and ready for future growth.

Current project status

Area

Status

What is done

What is next

Benchmarking

Completed

Top church website patterns reviewed; benchmark direction selected.

Continue using findings as the design and content standard.

Site structure

Completed

Navigation, page priorities, route layout, and visitor-first hierarchy are implemented.

Only minor wording or scope decisions remain.

Content planning

Substantially completed

Approved core identity, church story, mission, vision, beliefs, service times, address, ministry descriptions, and pastor bios are live on the site.

Finalize small wording refinements, sermon-specific media links, and any remaining FAQs or content notes.

Visual design

Strong pre-launch state

Approved brand direction is implemented, the transparent logo is integrated, and real worship imagery is now in use.

Add remaining leadership, venue, and community photography.

Development

Major phase completed

The Next.js site is now a polished, reusable, responsive website with real branding, real content, and practical forms in place.

Complete remaining integrations and launch setup.

QA

In progress

Production build passes, desktop review is strong, and core flows are in place.

Perform structured mobile, tablet, accessibility, and final link/content QA.

2. Phase-by-Phase Tracker

#

Phase

Status

Purpose

Key deliverables

Immediate focus

1

Discovery and benchmarking

Done

Research excellent church websites and define the upgrade direction.

Benchmark notes; gap analysis; preferred model.

Completed; maintain as reference benchmark.

2

Strategy and site architecture

Done

Define sitemap, navigation, audiences, and page goals.

Sitemap; nav structure; page purpose notes.

Confirm any remaining v1 scope details such as an Events page.

3

Content planning and copywriting

Substantially completed

Prepare page copy, CTAs, FAQs, and church messaging.

Homepage copy; page copy deck; content checklist.

Finalize small refinements and any additional sermon/ministry notes.

4

Branding and visual direction

Implemented

Set look and feel, colors, typography, image style, and UI language.

Design system; brand application; real logo usage.

Add more photography assets.

5

Wireframes and UX layout

Done

Map section order and visitor journey across major pages.

Wireframes; section maps; UX flow.

Use the live implementation as the baseline.

6

Frontend build

Completed

Build the website in Next.js with reusable components.

Working codebase; page templates; navigation; responsive layout.

No major frontend architecture work remains.

7

Content population

Substantially completed

Insert final content, photos, ministry details, and sermon assets.

Real church content is now implemented on the main pages.

Add remaining photos and sermon-specific links.

8

Integrations and functionality

Partially completed

Connect forms, WhatsApp, maps, YouTube, giving, and socials.

Verified social links, YouTube destination, and working first-version forms are in place.

Finalize giving link, map embed/pin, and sermon-specific media links.

9

QA and refinement

In progress

Test mobile layout, polish copy, fix issues, and improve performance.

Launch-ready website checklist.

Run structured mobile, tablet, desktop, accessibility, and content QA.

10

Launch

Not started

Deploy the site to the production domain and verify the live environment.

Live renewedlifeint.com website.

Deployment and live verification.

11

Post-launch growth

Not started

Continue SEO, content, testimonies, events, and future improvements.

Improvement backlog and monthly review rhythm.

Growth roadmap.

3. Workstreams and Detailed Task Breakdown

A. Strategy and structure

Confirm the final sitemap and primary navigation. — Completed in the current build.

Define page goals for Home, Plan Your Visit, About, Ministries, Sermons, Give, Events, and Contact. — Completed for the current route set; Events remains optional for v1.

Decide what content belongs on the homepage versus deeper pages. — Completed in the current UX structure.

B. Content and messaging

Write strong homepage headline, subheading, and call-to-action copy. — Implemented and refined.

Prepare a visitor-friendly What to Expect section. — Implemented on Plan Your Visit.

Rewrite About, ministries, and giving language with a warmer and clearer tone. — Implemented and refined.

Gather service times, address, contact details, and church distinctives. — Completed.

Apply approved church story, mission, vision, beliefs, and pastor bios. — Completed.

Add sermon-specific links and any final FAQ/ministry refinements. — Still outstanding.

C. Design and branding

Apply the final color palette, type scale, button styles, cards, and section spacing. — Implemented.

Integrate the final logo. — Completed using the transparent PNG logo.

Introduce real ministry photography. — Started with worship photography integrated into the homepage and About page.

Add leadership, venue, and community imagery. — Still outstanding.

D. Development

Refine the current Next.js prototype into a scalable component-based structure. — Completed.

Improve the homepage sections and supporting pages. — Completed.

Prepare reusable blocks for sermons, ministries, CTA banners, testimonials, and FAQs. — Core reusable structure is in place.

E. Integrations

Connect WhatsApp action links and contact forms. — WhatsApp is in place; first-version visitor and contact forms are working via email-assisted flow.

Embed or link sermons and live stream pathways. — YouTube channel is integrated as the primary watch destination; sermon-specific media links still need to be finalized.

Add maps/location details and giving links. — Directions are present; final map embed/pin and giving platform details are still needed.

Connect social platforms and practical visitor tools. — Verified Facebook, Instagram, and YouTube links are live.

F. Testing and launch readiness

Test all pages on mobile and desktop. — Desktop and build validation completed; structured responsive QA still required.

Check loading performance and accessibility basics. — Build passes; accessibility pass still needed.

Verify all buttons, forms, and links. — Internal route structure is verified; final live external links still need confirmation.

Do a final copy, spacing, and polish pass before launch. — In progress.

4. Deliverables Register

Deliverable

Description

Why it matters

Status

Benchmark report

Summary of the best church website examples and the selected direction.

Establishes the quality benchmark.

Done

Project tracker

This document, used as the management tracker for the full rebuild.

Keeps planning and execution aligned.

Done

Final sitemap

Confirmed page architecture and navigation.

Prevents confusion during content and build.

Done in current implementation; pending final stakeholder confirmation on any optional pages

Copy deck

Page-by-page approved website text.

Essential before full production build.

Core content implemented; only minor refinements remain

Design system

Colors, typography, buttons, section styles, and UI rules.

Keeps the site consistent and professional.

Completed

Pre-launch website

Responsive Next.js site with real branding and core content.

Main v1 build deliverable.

Completed to late pre-launch state; integrations and QA remain

Launch checklist

QA, link checks, mobile checks, deployment tasks.

Reduces launch mistakes.

In progress

5. Decisions, Risks, and Dependencies

Key decisions already made

• The website is being rebuilt in Next.js rather than simply restyling the old site.

• The new site focuses on a strong first-visitor journey rather than a template-style homepage.

• The benchmark direction is adapted to Renewed Life’s current size and needs rather than copied feature-for-feature.

• A dedicated Plan Your Visit page is part of the core v1 structure.

• The current implementation uses reusable sections and a maintainable design system.

• Renewed Life is the primary display name on the website, while Renewed Life International remains the legal and formal ministry name.

Main risks to manage

Risk

Potential impact

Mitigation action

Level

Missing imagery

The site can still feel unfinished without leadership, venue, and broader community photography.

Continue asset collection and place high-value imagery before launch.

High

Integration delays

Giving, maps, and sermon-specific links can block full launch readiness.

Finalize these in a focused Phase 8 pass.

High

Feature creep

Too many add-ons can delay launch.

Keep v1 focused on the core visitor journey and launch essentials.

High

Weak final QA

A polished website can still ship with avoidable issues if device and accessibility QA are skipped.

Run a structured launch checklist across devices and user journeys.

High

Dependencies

• Final giving pathway and any banking/reference instructions

• Confirmed map embed or final share pin

• Sermon-specific links for featured/archive content

• Leadership, venue, and community imagery

6. Immediate Next-Step Tracker

#

Next action

Reason

Target phase

1

Add remaining leadership, venue, and community photos.

The website now has real branding and worship imagery, but broader photography will complete the trust and warmth of the experience.

Phase 7

2

Confirm the final giving link and exact map embed/pin.

These are still needed for true launch readiness.

Phase 8

3

Finalize sermon-specific media links.

This improves the polish and usefulness of the sermons archive.

Phase 8

4

Run full QA across mobile, tablet, and desktop, including accessibility basics.

This turns the pre-launch build into a launch-ready site.

Phase 9

5

Prepare deployment and launch checklist.

The site is near launch and needs production rollout planning next.

Phase 10

Recommended project focus right now: complete the remaining integrations, finish photography population, run structured QA, and prepare for deployment. The project is now in late pre-launch refinement rather than prototype build.